## Sheet1
Project name | Estimate | PM | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01
Key Street Phase 1 NB o/slip signals | £1M | Andy Moreton | 2018-11-01: outline design & scheme planning; 2019-03-01: detailed design & approvals; 2019-09-01: construction
Key Street Phase 2 freeflow lane and new SB onslip | £5M | Andy Moreton | 2018-11-01: outline design & scheme planning; 2019-03-01: detailed design & approvals; 2020-10-01: Construction (tbc)
Grovehurst Road | £34M | Andy Moreton | 2018-11-01: outline design; 2019-05-01: detailed design, approvals, procurement; 2020-10-01: Advance works/mitigations (tbc)
Thames Way dualling | £8.5M | Andy Moreton | 2018-11-01: feasibility; 2019-03-01: outline/detailed design, approvals, procurement; 2020-04-01: construction
UTMC - Kent Thameside | £3.5M | Andy Moreton | 2018-12-01: feasibility; 2019-06-01: future progression tbc
Fastrack Full Network - Bean Road Tunnels | £12M | Graham Killick | 2018-11-01: outline/reference design, approvals, procurement; 2019-10-01: construction ( design & build)
Fastrack Full Network - Feasibility Schemes | £27.7M | Graham Killick | 2018-11-01: feasibility; 2019-01-01: future progression tbc
Herne Relief Road - Bullockstone Improvement Scheme | £7.69M | Victoria Soames | 2018-11-01: outline; 2019-07-01: planning; 2019-11-01: detailed design and procurement; 2021-03-01: Construction
A249 Bearsted Road Maidstone incl M20 J7 | Current arrangement | Russell Boorman | 2018-11-01: Detailed Design; 2019-02-01: Procurement & Contract Award; 2019-06-01: Mobilisation; 2019-09-01: construction
A20 Coldharbour Roundabout/A20 London Road Hall Road | Current arrangement | Russell Boorman | 2018-11-01: Outline Design; 2019-08-01: Detailed Design; 2020-01-01: Procurement; 2020-05-01: Mobilisation; 2020-08-01: Construction
A229 Loose Road Corridor | Current arrangement | Russell Boorman | 2018-11-01: Outline Design; 2019-05-01: Detailed Design; 2019-11-01: Procurement; 2020-04-01: Mobilisation; 2020-07-01: Construction
A20 Ashford Road Maidstone Willington Street | Current arrangement | Russell Boorman | 2018-11-01: Outline Design; 2019-02-01: Detailed Design; 2019-08-01: Procurement; 2019-12-01: Mobilisation; 2020-03-01: Construction
B2246 Hermitage Lane incl Fountain Lane | Current arrangement | Russell Boorman | 2018-11-01: Feasibility
Westwood Relief Strategy | Current arrangement | Russell Boorman | 2018-11-01: Feasibility
A20 Ashford Road Maidstone New Cut Road | Current arrangement | Russell Boorman | 2018-11-01: Feasibility; 2019-04-01: Outline Design; 2019-10-01: Detailed Design; 2020-04-01: Procurement; 2020-08-01: Mobilisation; 2020-11-01: Construction?
Lower Road Phase 1 | £1.86m | Richard Shelton | 2018-11-01: construction
Lower Road Phase 2 | £4.8m | Richard Shelton | 2018-11-01: detailed design & approvals; 2019-02-01: construction
Sturry Link Road | £29.6m | Richard Shelton | 2018-11-01: outline design & scheme planning; 2019-06-01: detailed design & approvals; 2020-02-01: construction
Gravesend Bus Hub | £2.7m | RS / Annette Bonner | 2018-11-01: outline design; 2019-02-01: detailed design & approvals; 2019-09-01: construction
Rathmore Road | completed | Richard Shelton | 2019-01-01: After scheme Monitoring
M20J4 | completed | Richard Shelton | 2019-01-01: After scheme Monitoring
Wincheap - Western Link | £2.4m | Richard Shelton/ Ben | 2019-01-01: outline design & scheme planning; 2019-07-01: detailed design & approvals; 2020-08-01: construction
St Clements Way | £6m | Barry Stiff | 2018-11-01: construction; 2020-04-01: After Scheme Monitoring
A28 Chart Road | £24m | Barry Stiff | 2018-11-01: Detailed design; 2019-02-01: Mobilisation & Construction if Developer provides funding by 31 January 2019 otherwise construction will be deferred until 2022/2023
Dover BRT | £15m | Barry Stiff | 2018-11-01: feasibility; 2019-01-01: Detailed Design, Planning & Procurement (subject to approval of HIF Funding in December 18); 2019-11-01: Mobilisation; 2020-02-01: Construction
Manston Green Junction | £6m | Barry Stiff | 2018-11-01: feasibility; 2019-01-01: Detailed Design, Planning & Procurement (subject to approval of HIF Funding in December 18); 2019-11-01: Mobilisation; 2020-02-01: Construction
Columbus Avenue Extension | £8m | Barry Stiff | 2018-11-01: feasibility; 2019-01-01: Future progression of scheme reliant on funding
Manston Road to Haine Road Link (Could be 1, 2 or 3 sections) | £6m to £24m | Barry Stiff | 2018-11-01: feasibility; 2019-04-01: Future progression of scheme reliant on funding and outcome of DCO
A256 Sandwich - A257 & A258 Junctions | £6-8m | Barry Stiff | 2019-01-01: Feasibility; 2019-05-01: Future progression of scheme reliant on funding and outcome of DCO