## Slide 1
South East & Mid Wales Collaborative Civil Engineering and Highways Construction Framework (SEWH)
Client-Contractor Meeting
Friday 22nd November 2024

## Slide 2: Presentation Agenda
Welcome
Framework Update
Pipeline figures for 2024-2025
Pipeline updates from clients
Ed Evans of CECA
AOB

## Slide 3: Framework Update
Awarded Notices
Insurances
Levy Collection
Rate Review
Notes: We’ve been actively collecting awarded notices over the past few months. Thank you to everyone who has responded. For those who haven’t yet, the team will be in touch shortly to follow up
Contractor – We appreciate the timely responses to insurance update requests that contractors would have received . If you’ve not yet provided the required documents, please prioritise this to ensure compliance.
Contractor & Client – Thank you for engaging with the recent levy collection emails, I know there has been a lot of these requested. If you haven’t responded yet or have concerns about discrepancies, please contact the team so we can resolve any issues promptly. I’d also like to remind everyone to review their user agreements to ensure clarity on how the levy fee is calculated
Rate Review – We’re finalising the rate review process. Rates for Lots 1-9 are ready, and we’re awaiting the remaining lots. Once these have been finalised, you’ll receive confirmation of when the updated rates go live

## Slide 4
Chart: Awarded projects 2024
| Lot 1 | Lot 2 | Lot 3 | Lot 4 | Lot 5 | Lot 6 | Lot 7 | Lot 8 | Lot 9 | Lot 10 | Lot 11 | Lot 14 | Lot 15
 | 9 | 4 | 12 | 9 | 5 | 11 | 8 | 9 | 8 | 1 | 1
Notes: The awarded contracts reflects a strong distribution of work across most lots. However, there has been limited activity on Lot 8 and Lot 9, which are our higher value lots. I can imagine this is expected with limited budgets

## Slide 5
Chart: Pipeline Projects by Lot (2024-2025)
| Lot 1 | Lot 2 | Lot 3 | Lot 4 | Lot 5 | Lot 6 | Lot 7 | Lot 8 | Lot 9 | Lot 10 | Lot 11 | Lot 14 | Lot 15
 | 5 | 2 | 6 | 2 | 13 | 3 | 2 | 5 | 3 | 0
Notes: From the pipelines provided – this is the distribution of work over the next 12 months or so. I must add that there are about 20 projects not included on this graph, in which the clients haven’t decided which lot it will be on, we can update these when we receive the information.

## Slide 6
Chart: Pipeline Value for each Lot
| Lot 1 | Lot 2 | Lot 3 | Lot 4 | Lot 5 | Lot 6 | Lot 7 | Lot 8 | Lot 9 | Lot 10 | Lot 11 | Lot 14 | Lot 15
 | 1515000 | 150000 | 410000 | 2710000 | 402000 | 16232000 | 8450000 | 30000000 | 875000 | 7400000 | 165000 | 345000
Notes: Here’s the value of work going through each lot. Again quite varied, but its promising to see that there’s work planned within lot 8 and Lot 9 going forward.

## Slide 7
Chart: Pipeline Call Off Dates in 2024-2025
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct
 | 5 | 2 | 2 | 3 | 1 | 5 | 9 | 4 | 1
Notes: Here’s an estimated timeline of mini comps off the framework over the next 8 months. As you can see there is an upward trend of projects into the new financial year which is what we’d expect. Again, this graph is missing those projects in which clients haven’t provided a call off date, we will look make sure this is updated when we have that information.

## Slide 8: Clients
Client | Clients Attending
Cardiff Council | Gareth Jones Neil Pugh Andrew Powell
Powys County Council | Adam Parry
Newport County Council | Michael Owen Meirion Humpheys
Monmouthshire County Council | Rob Davies
Vale of Glamorgan Council | Nathan Thomas Craig Howell
Torfaen County Borough Council | Clare Woodward Sarah Herbert
Bridgend County Borough Council | Tahir Saleem
Rhondda Cynon Taf County Borough Council | Andrew Stone David Afia

## Slide 9: Cardiff CC - Future Pipeline Neil Pugh
Lot | Description of works | Estimate Mini comp Date | Estimate mini comp end date | Expected start date | Estimated £ of Works | Likelihood Red Amber Green
3 | Engineers Streets | 01/11/2024 | 01/12/2024 | 01/01/2025 | £ 115,000.00 | 
3 | Neville Street | 01/11/2024 | 01/12/2024 | 01/01/2025 | £ 100,000.00 | 
8 | Trowbridge Green | 01/11/2024 | 01/01/2024 | 01/04/2025 | £ 2,000,000.00 | 
6 | Central Square (Tactiles) | 01/11/2024 | 01/12/2024 | 01/01/2025 | £ 240,000.00 | 
3 | Riverside CPZ | 01/12/2024 | 01/02/2025 | 01/05/2025 | £ 150,000.00 | 
7 | New Willows (AT Route) | 01/05/2025 | 01/07/2025 | 01/11/2025 | £ 1,700,000.00 | 
9 | City Centre - (Boulevard De Nantes - Newport Rd) | 01/06/2025 | 01/08/2025 | 01/01/2026 | £ 7,000,000.00 | 
9 | Eastern Bus Corridor - Newport Rd (Link A) | 01/06/2025 | 01/08/2025 | 01/01/2026 | £ 7,000,000.00 | 
7 | North Rd/Corbett Road | 01/06/2025 | 01/08/2025 | 01/01/2026 | £ 1,800,000.00 | 
Notes: Please note the introduction of the Likelihood column. Please see below guidance:
Green (High Likelihood):
Contract has been fully scoped and approved.
Funding is secured
Minimal to no obstacles expected before execution.
Amber (Moderate Likelihood)
Some aspects still need final approval (e.g., partial scoping, or awaiting confirmation on funding).
Dependencies or risks are identified, but they are manageable or in the process of resolution.
Red (Low Likelihood)
Early discussions or conceptual phase.
Significant unknowns or unresolved issues (e.g., no clear funding)

## Slide 10: Cardiff CC - Future Pipeline Neil Pugh
Lot | Description of works | Estimate Mini comp Date | Estimate mini comp end date | Expected start date | Estimated £ of Works | Likelihood Red Amber Green
8 | Eastern Bus Corridor - Newport Rd (Broadway) (Link B) | TBC | TBC | TBC | £ 3,450,000.00 | 
8 | Roath Park Cycleway - (Albany/Richmond) | TBC | TBC | TBC | £ 3,000,000.00 | 
7 | Hailey Park | TBC | TBC | TBC | £ 632,000.00 | 
3 | Pentyrch Primary School | TBC | TBC | TBC | £ 150,000.00 | 
6 | James St/Adelaide Street | TBC | TBC | TBC | £ 162,000.00 | 
 | Castle Street | TBC | TBC | TBC | TBC | 
 | CW4.2 - Llandaff | TBC | TBC | TBC | TBC | 
 | Llanrumney Avenne | TBC | TBC | TBC | TBC | 
 | Ely Road Ends Phase 4 | TBC | TBC | TBC | TBC | 
Notes: Please note the introduction of the Likelihood column. Please see below guidance:
Green (High Likelihood):
Contract has been fully scoped and approved.
Funding is secured
Minimal to no obstacles expected before execution.
Amber (Moderate Likelihood)
Some aspects still need final approval (e.g., partial scoping, or awaiting confirmation on funding).
Dependencies or risks are identified, but they are manageable or in the process of resolution.
Red (Low Likelihood)
Early discussions or conceptual phase.
Significant unknowns or unresolved issues (e.g., no clear funding)

## Slide 11: Cardiff CC - Future Pipeline Andrew Greener, Gareth Jones, Andrew Powell
Lot | Description of works | Estimate Mini comp Date | Estimate mini comp end date | Expected start date | Estimated £ of Works | Likelihood Red Amber Green
10 | Carriageway Resurfacing |  |  |  | £250000.00 | Amber
3 | Footway Resurfacing |  |  |  | £150000.00 | Amber
Notes: Please note the introduction of the Likelihood column. Please see below guidance:
Green (High Likelihood):
Contract has been fully scoped and approved.
Funding is secured
Minimal to no obstacles expected before execution.
Amber (Moderate Likelihood)
Some aspects still need final approval (e.g., partial scoping, or awaiting confirmation on funding).
Dependencies or risks are identified, but they are manageable or in the process of resolution.
Red (Low Likelihood)
Early discussions or conceptual phase.
Significant unknowns or unresolved issues (e.g., no clear funding)

## Slide 12: RCT - Future Pipeline David Afia, Andrew Stone
Lot | Description of works | Estimate Mini comp Date | Estimate mini comp end date | Expected start date | Estimated £ of Works | Likelihood Red Amber Green
11 | Carriageway surface treatment 2024/25 | 01/04/2024 | 01/05/2024 | 01/05/2024 | £ 500,000.00 | 
10 | Carriageway resurfacing 2024/25 Batch 2 | 01/06/2024 | 01/07/2024 | 01/07/2024 | £ 500,000.00 | 
10 | Carriageway resurfacing 2024/25 Batch 3 | 01/09/2024 | 01/10/2024 | 01/10/2024 | £ 500,000.00 | 
7 | Afon Cynon Bridge | 01/10/2024 | 01/11/2024 | 01/05/2025 | £ 1,500,000.00 | 
 | A4058 Hillside Porth Wall | 01/12/2024 | 01/01/2025 | 01/06/2025 | £ 750,000.00 | 
7 | Turberville Road - FAS | 02/12/2024 | 01/02/2025 | 01/07/2025 | £ 600,000.00 | 
7 | Cardiff Road / Maes y Fynnon - Attenuation Pond | 01/01/2025 | 01/03/2025 | 01/07/2025 | £ 600,000.00 | 
7 | Arfron Terrace, Tyerstown - FAS | 01/02/2025 | 01/03/2025 | 01/06/2025 | £ 1,200,000.00 | 
 | King Georges Field | 01/02/2025 | 01/03/2025 | 01/07/2025 | tbc | 
Notes: Please note the introduction of the Likelihood column. Please see below guidance:
Green (High Likelihood):
Contract has been fully scoped and approved.
Funding is secured
Minimal to no obstacles expected before execution.
Amber (Moderate Likelihood)
Some aspects still need final approval (e.g., partial scoping, or awaiting confirmation on funding).
Dependencies or risks are identified, but they are manageable or in the process of resolution.
Red (Low Likelihood)
Early discussions or conceptual phase.
Significant unknowns or unresolved issues (e.g., no clear funding)

## Slide 13: RCT - Future Pipeline David Afia, Andrew Stone
Lot | Description of works | Estimate Mini comp Date | Estimate mini comp end date | Expected start date | Estimated £ of Works | Likelihood Red Amber Green
 | Brynmair Rd | 01/03/2025 | 01/04/2025 | 01/05/2025 | tbc | 
5 | Windsor Place Footbridge | 01/04/2025 | 01/05/2025 | 01/06/2025 | £ 350,000.00 | 
 | Treorchy to Treherbert Active Travel Route | 01/04/2025 | 01/05/2025 | 01/07/2025 | £ 800,000.00 | 
7 | Taff Trail South of Nant Cae Dwg footbridge | 01/05/2025 | 01/06/2025 | 01/08/2025 | £ 1,500,000.00 | 
7 | Cynon Trail Cwmbach | 01/05/2025 | 01/06/2025 | 01/07/2025 | £ 1,100,000.00 | 
7 | Rhondda Fach Ph 3 | 01/05/2025 | 01/06/2025 | 01/07/2025 | £ 2,300,000.00 | 
11 | Rhondda Fach Ph 5 | 01/05/2025 | 01/06/2025 | 01/08/2025 | £ 4,700,000.00 | 
7 | Aberdare Town Centre enhancements - Active Travel | 01/05/2025 | 01/06/2025 | 01/08/2025 | £ 1,000,000.00 | 
5 | Mill Street, Tonyrefail | 01/05/2025 | 01/06/2025 | 01/08/2025 | £ 250,000.00 | 
5 | Ely Brook, Cilfynydd - culvert inlet | 01/05/2025 | 01/06/2025 | 01/08/2025 | £ 250,000.00 | 
Notes: Please note the introduction of the Likelihood column. Please see below guidance:
Green (High Likelihood):
Contract has been fully scoped and approved.
Funding is secured
Minimal to no obstacles expected before execution.
Amber (Moderate Likelihood)
Some aspects still need final approval (e.g., partial scoping, or awaiting confirmation on funding).
Dependencies or risks are identified, but they are manageable or in the process of resolution.
Red (Low Likelihood)
Early discussions or conceptual phase.
Significant unknowns or unresolved issues (e.g., no clear funding)

## Slide 14: RCT - Future Pipeline David Afia, Andrew Stone
Lot | Description of works | Estimate Mini comp Date | Estimate mini comp end date | Expected start date | Estimated £ of Works | Likelihood Red Amber Green
 | High Street, Ynysbwl | 01/05/2025 | 01/06/2025 | 01/08/2025 | tbc | 
 | Llanwit Fardre Closed ProW Footbridge Replacement | 01/05/2025 | 01/05/2025 | 01/06/2025 | £ 100,000.00 | 
 | Commercial Street Footbridge Refurbishment, Aberdare | 01/05/2025 | 01/05/2025 | 01/06/2025 | £ 400,000.00 | 
 | Castellau Road ProW Footbridge Replacement | 01/05/2025 | 01/05/2025 | 01/06/2025 | £ 100,000.00 | 
 | Crossbychan Bridge | 01/05/2025 | 01/05/2025 | 01/06/2025 | £ 500,000.00 | 
5 | A4058 Dinas | 01/06/2025 | 01/07/2025 | 01/09/2025 | £ 200,000.00 | 
 | Rosedale Terrace | 01/06/2025 | 01/07/2025 | 01/08/2025 | tbc | 
5 | St Lukes Rd, Llwyncelyn - culvert | 01/07/2025 | 01/08/2025 | 01/10/2024 | £ 160,000.00 | 
 | Dynea Road, Rhydyfelin - Retaining Wall Remedial Works | 01/09/2025 | 01/08/2025 | 01/09/2025 | £ 150,000.00 | 
9 | Pentre FAS | 01/02/2026 | 01/02/2026 | 01/05/2026 | £ 7,000,000.00 | 
Notes: Please note the introduction of the Likelihood column. Please see below guidance:
Green (High Likelihood):
Contract has been fully scoped and approved.
Funding is secured
Minimal to no obstacles expected before execution.
Amber (Moderate Likelihood)
Some aspects still need final approval (e.g., partial scoping, or awaiting confirmation on funding).
Dependencies or risks are identified, but they are manageable or in the process of resolution.
Red (Low Likelihood)
Early discussions or conceptual phase.
Significant unknowns or unresolved issues (e.g., no clear funding)

## Slide 15: RCT - Future Pipeline David Afia
Lot | Description of works | Estimate Mini comp Date | Estimate mini comp end date | Expected start date | Estimated £ of Works | Likelihood Red Amber Green
7 | Llanharan active travel route | 01/04/2026 | 01/05/2026 | 01/06/2026 | £ 800,000.00 | 
9 | Treorchy FAS | 01/04/2026 | 01/05/2026 | 01/07/2026 | £ 9,000,000.00 | 
 | Abetonllwyd Rd, Treherert | 01/04/2026 | 01/05/2026 | 01/08/2026 | tbc | 
5 | Nant Gwarw Ph 2 | 01/05/2026 | 01/06/2026 | 01/08/2026 | £ 1,500,000.00 | 
7 | Oaklands Terrace Cilfynydd | 01/05/2026 | 01/06/2026 | 01/08/2026 | £ 1,500,000.00 | 
 | Afon Cynon / Wellington Street | 01/05/2026 | 01/06/2026 | 01/07/2026 | tbc | 
 | Cefnpennar Rd FAS | 01/05/2026 | 01/06/2026 | 01/08/2026 | tbc | 
Notes: Please note the introduction of the Likelihood column. Please see below guidance:
Green (High Likelihood):
Contract has been fully scoped and approved.
Funding is secured
Minimal to no obstacles expected before execution.
Amber (Moderate Likelihood)
Some aspects still need final approval (e.g., partial scoping, or awaiting confirmation on funding).
Dependencies or risks are identified, but they are manageable or in the process of resolution.
Red (Low Likelihood)
Early discussions or conceptual phase.
Significant unknowns or unresolved issues (e.g., no clear funding)

## Slide 16: Monmouthshire - Future Pipeline Rob Davies
Lot Number | Description of works | Estimate Mini comp Date | Estimate mini comp end date | Expected start date | Estimated £ of Works | Likelihood Red Amber Green
10 | Wyebridge Resurfacing, Monmouth | 01/02/2024 | 01/03/2024 | 01/03/2025 | £590,000.00 | AMBER
4 | Bus Turnaround Infrastructure | 01/04/2025 | 01/05/2025 | TBC | £180,000.00 | AMBER
 | Active Travel Route | 2025 | 2025 |  | £350,000.00 | RED
4 | Monmouth Road, Usk -Active Travel Route. | 01/01/2025 | 01/01/2025 | 01/02/2025 | £230,000.00 | GREEN
10 | Twyn Sq resurfacing, Usk | 01/11/2024 | 01/01/2025 | 01/01/2025 | £35,000.00 | GREEN
Notes: Please note the introduction of the Likelihood column. Please see below guidance:
Green (High Likelihood):
Contract has been fully scoped and approved.
Funding is secured
Minimal to no obstacles expected before execution.
Amber (Moderate Likelihood)
Some aspects still need final approval (e.g., partial scoping, or awaiting confirmation on funding).
Dependencies or risks are identified, but they are manageable or in the process of resolution.
Red (Low Likelihood)
Early discussions or conceptual phase.
Significant unknowns or unresolved issues (e.g., no clear funding)

## Slide 17: Newport - Future Pipeline Michael Owen and Meirion Humpheys
Lot Number | Description of works | Estimate Mini comp Date | Estimate mini comp end date | Expected start date | Estimated £ of Works | Likelihood Red Amber Green
 | C’way Preservation treatments | 01/04/2025 | 01/05/2025 | 01/06/2025 | £390000.00 | Amber
 | C-way Resurfacing works | 01/05/2025 | 01/06/2025 | 01/07/2025 | £260000.00 | Amber
 | Shared use & pedestrian improvements | 01/06/2025 | 01/08/2025 | 01/09/2025 | £1000000.00 | Red
 | Shared use & pedestrian improvements | 01/06/2025 | 01/07/2025 | 01/09/2025 | £300000.00 | Amber
 | EV Charging Facilities | 01/02/2025 | 01/03/2025 | 01/05/2025 | £175000.00 | Amber
Notes: Please note the introduction of the Likelihood column. Please see below guidance:
Green (High Likelihood):
Contract has been fully scoped and approved.
Funding is secured
Minimal to no obstacles expected before execution.
Amber (Moderate Likelihood)
Some aspects still need final approval (e.g., partial scoping, or awaiting confirmation on funding).
Dependencies or risks are identified, but they are manageable or in the process of resolution.
Red (Low Likelihood)
Early discussions or conceptual phase.
Significant unknowns or unresolved issues (e.g., no clear funding)

## Slide 18: Bridgend- Future Pipeline Tahir Saleem
Lot Number | Description of works | Estimate Mini comp Date | Estimate mini comp end date | Expected start date | Estimated £ of Works | Likelihood Red Amber Green
Notes: Please note the introduction of the Likelihood column. Please see below guidance:
Green (High Likelihood):
Contract has been fully scoped and approved.
Funding is secured
Minimal to no obstacles expected before execution.
Amber (Moderate Likelihood)
Some aspects still need final approval (e.g., partial scoping, or awaiting confirmation on funding).
Dependencies or risks are identified, but they are manageable or in the process of resolution.
Red (Low Likelihood)
Early discussions or conceptual phase.
Significant unknowns or unresolved issues (e.g., no clear funding)

## Slide 19: Torfaen - Future Pipeline Clare Woodward and Sarah Herbert
Lot Number | Description of works | Estimate Mini comp Date | Estimate mini comp end date | Expected start date | Estimated £ of Works | Likelihood Red Amber Green
Notes: Please note the introduction of the Likelihood column. Please see below guidance:
Green (High Likelihood):
Contract has been fully scoped and approved.
Funding is secured
Minimal to no obstacles expected before execution.
Amber (Moderate Likelihood)
Some aspects still need final approval (e.g., partial scoping, or awaiting confirmation on funding).
Dependencies or risks are identified, but they are manageable or in the process of resolution.
Red (Low Likelihood)
Early discussions or conceptual phase.
Significant unknowns or unresolved issues (e.g., no clear funding)

## Slide 20: Vale of Glamorgan - Future Pipeline Nathan Thomas and Craig Howell
Lot Number | Description of works | Estimate Mini comp Date | Estimate mini comp end date | Expected start date | Estimated £ of Works | Likelihood Red Amber Green
Notes: Please note the introduction of the Likelihood column. Please see below guidance:
Green (High Likelihood):
Contract has been fully scoped and approved.
Funding is secured
Minimal to no obstacles expected before execution.
Amber (Moderate Likelihood)
Some aspects still need final approval (e.g., partial scoping, or awaiting confirmation on funding).
Dependencies or risks are identified, but they are manageable or in the process of resolution.
Red (Low Likelihood)
Early discussions or conceptual phase.
Significant unknowns or unresolved issues (e.g., no clear funding)

## Slide 21
Ed Evans
Civil Engineering Contractors Association
(CECA) Wales

## Slide 22
Open Discussion
AOB
Next Pipeline Update

## Slide 23: Contacting the Team
Website: www.sewh.co.uk
Email: sewhighways@cardiff.gov.uk
Telephone: 02920 873701
Team Members
Luke Howells – Framework Manager
Upanish Mallissery - Category Specialist
Bradley Moses – Category Support Officer